# AI4U Customer Service Agent — Executive Briefing

## 1. The opportunity

The European Distribution Center (EDC) customer-service team handles a high volume of inbound emails every day — order status, shipment tracking, and document requests (packing lists, invoices, proof of delivery).

Today every one is manual. A rep opens the email, reads it, extracts the order number, logs into SAP, works out who the customer is and which country rules apply, downloads the right documents, drafts a reply, attaches the files, and sends. Minutes of skilled effort per email, repeated hundreds of times, on work that is mostly lookup-and-assemble.

The agent automates the assembly and keeps the human in control. It reads the email, understands the request, retrieves the data and documents from SAP, and hands the rep a finished draft to review and approve. The rep's job shifts from doing the lookup to approving the result — seconds instead of minutes.

This is being built under SAP's "AI for You" (AI4U) program, which seed-funds customers to adopt SAP's AI portfolio — so SAP is an active partner and part of the investment.

## 2. What is already working (proven, not slideware)

A functioning application is deployed on J&J's BTP sandbox today and integrated with SAP AI Core. It demonstrably does the end-to-end loop for the email-and-draft stage:

| Capability | Status |
| --- | --- |
| Reads a customer email — picked from Outlook, forwarded, or pasted | Working |
| Identifies the correct person to reply to (even from a forwarded email, in multiple European languages) | Working |
| Uses AI (SAP AI Core) to detect the request type and extract the order number | Working |
| Drafts a professional reply, in the customer's language | Working |
| Rep reviews, edits, approves — full audit trail | Working |
| Sends the reply through Outlook (Microsoft Graph), from the rep, when connected | Working |
| Runs as one deployable unit on BTP Cloud Foundry | Working |

## 3. Roadmap to production

| Phase | What it delivers | Business value | Status |
| --- | --- | --- | --- |
| P0 — Email + AI draft | Ingest email, detect intent, draft reply, human approve, send | Proves the pipeline; retires the email-integration risk | Done |
| P1 — Connect real J&J mail | Live J&J mailbox via Outlook/Graph; forward-to-mailbox auto-ingest | Reps use it on real inbound mail | ⏳ Gated by IT app-registration |
| P2 — SAP data & documents | Pull order status, delivery, packing list, invoice, shipment docs from S/4HANA + EWM and attach them | The core value — full answers, real documents, no manual SAP work | 🔜 Needs integration workstream + SAP APIs |
| P3 — Business rules | Entitlement engine: who is asking → which documents they may receive | Compliance / correct disclosure per requester & region | 🔜 Needs a business rule owner |
| Productionize & scale | App-level security (XSUAA), production database (HANA Cloud), audit/validation, monitoring, analytics, auto-ingestion, more franchises | Enterprise-grade, measurable, multi-team rollout | 🔜 |

## 4. Effort & cost

Planning-level. See the companion sheet AI4U-CS-Agent-Roadmap-Cost.csv

### Effort (person-weeks, ranges)

| Phase | Dev effort | Notes |
| --- | --- | --- |
| P0 | spent | Complete |
| P1 | 2–3 wks | Low dev; the real wait is IT approval, not coding |
| P2 | 4–10 wks | Largest — SAP integration + document retrieval, across the integration team and front end |
| P3 | 11–12 wks | Security, prod DB, audit, analytics, hardening — more if GxP validation applies |
| To production | 13–16 wks | Across workstreams; ~3–6 months calendar depending on approvals & SAP access |

### Cost drivers (not yet priced — flagged for finance)

| Driver | Type | Notes |
| --- | --- | --- |
| SAP BTP entitlements — Cloud Foundry, HANA Cloud, Integration Suite | Recurring | AI Core + CF already in the sandbox; HANA Cloud & Integration Suite needed for production. TBD via SAP licensing. |
| SAP AI Core token consumption | Recurring, volume-based | Scales with email volume — the main run-rate variable. Small per email; sizeable at full volume. |
| Microsoft — dedicated mailbox / licensing | Recurring | For the shared-mailbox auto-ingest model; TBD. |

## 5. Dependencies & decisions needed (the asks)

| # | Need | Why it matters | Owner |
| --- | --- | --- | --- |
| 1 | Azure AD app registration for the mailbox (delegated Graph) | Gates P1 — connecting real J&J email. Long lead in security review. | J&J IT / Security |
| 2 | SAP dev/sandbox with EDC order data + agreement on the API layer over S/4/EWM | Gates P2 — the core value. Likely the #1 schedule risk. | SAP integration team |

## 6. The value case (framework — plug in EDC's real numbers)

The ROI is a simple, defensible calculation once EDC provides two inputs:

Annual hours saved = emails/day × working days × minutes saved per email ÷ 60
Annual value       = annual hours saved × loaded hourly cost of a CS rep

Example placeholder (illustrative only — replace with real figures):

- 200 emails/day × 250 days × 6 min saved ÷ 60 = 5,000 hours/year

- × a loaded rep rate = the headline savings number

Beyond hours: faster response to customers, fewer errors in document selection, and reps freed for complex, judgment work. The agent handles the repetitive lookup; people handle the exceptions.

Action: get EDC's actual daily email volume and average handle time — those two numbers turn this framework into the VP's headline slide.